## Sheet1
SCHEDULE (WEEK ENDING)
TASK ID | ENG RQMT | TASK DESCRIPTION | RESPONSIBLE TEAM MEMBER | PLANNED TOTAL HOURS | PLANNED COST | PLANNED START DATE | ACTUAL START DATE | PLANNED END DATE | ACTUAL END DATE | 2020-01-25 | 2020-02-01 | 2020-02-08 | 2020-02-15 | 2020-02-22 | 2020-02-29 | 2020-03-07 | 2020-03-14 | 2020-03-21 | 2020-03-28 | 2020-04-04 | 2020-04-11 | 2020-04-18 | 2020-04-25 | 2020-05-02 | ACTUAL TOTAL HOURS | ACTUAL COST
|  | Plan and Schedule | KP | 15 | 225 | 2020-01-25 | 2020-01-31 | 2020-02-03 | 2020-02-03 | [15 empty] | 8 | 120 | bar: 2020-02-08
|  | Test Plan | KP | 15 | 225 | 2020-02-10 | 2020-02-22 | 2020-02-26 | [16 empty] | 1 | 15 | bar: 2020-02-29
|  | Test Report | KP | 20 | 300 | 2020-03-02 | 2020-03-20 | 2020-03-24 | 2020-03-24 | [15 empty] | 5 | 75 | bar: 2020-03-28
|  | Final Report | KP | 35 | 525 | 2020-03-30 | 2020-04-21 | 2020-04-13 16:00 | 2020-04-29 | [15 empty] | 26 | 390 | bar: 2020-05-02
|  | Final Presentation & Demo | KP | 30 | 450 | 2020-03-30 | 2020-04-22 | 2020-04-12 | 2020-04-29 | [15 empty] | 22 | 330 | bar: 2020-05-02
1 |  | Commercial Detection Program | KP | 103 | 1545 | 2020-01-24 | 2020-01-24 | 2020-03-03 | [16 empty] | 35 | 525
1.1.1 | 2, 3 | Read in audio via 3.5mm and plot using Matplotlib | KP | 3 | 45 | 2020-01-24 | 2020-01-24 | 2020-01-24 | 2020-01-24 | [15 empty] | 3 | 45
X
1.1.2 | 2, 3 | Plot audio input continously | ZT | 2 | 30 | 2020-01-27 | 2020-01-31 | 2020-01-31 | 2020-01-31 | [15 empty] | 1.5 | 22.5
X
1.2 | 2 | Implement 2-3 audio cues | KP | 30 | 450 | 2020-02-03 | 2020-02-14 | 2020-02-16 | [16 empty] | 50 | 750
1.2.1 | 2 | Implement Silent Frame detection | ZT | 5 | 75 | 2020-02-03 | 2020-02-14 | 2020-02-07 16:00 | [16 empty] | 30 | 450
1.2.2 | 2 | Implement Volume Spike detection | ZT | 5 | 75 | 2020-02-03 | 2020-02-14 | 2020-02-07 16:00 | [16 empty] | 20 | 300
1.2.3 | 2 | Implement STD. Dev. Of Avg. Volume | KP | 20 | 300 | 2020-02-03 |  | 2020-02-12 16:00 | [16 empty] | 0 | 0
1.3 | 3 | Read IR Receiver and store value transmitted by remote | ZT | 5 | 75 | 2020-02-28 |  | 2020-03-03 16:00 | [16 empty] | 0 | 0
1.3.1 | 3 | Mode button at init. Default to 0 (mute commercials) | KP | 2 | 30 | 2020-02-28 |  | 2020-03-02 16:00 | [16 empty] | 0 | 0
1.3.2 | 3 | Read mode button press, change value to 1 (50% volume reduction) | ZT | 2 | 30 | 2020-02-28 |  | 2020-03-02 16:00 | [16 empty] | 0 | 0
1.3.3 | 3 | Start/Stop button must start and stop commercial detection program | KP | 2 | 30 | 2020-02-28 |  | 2020-03-02 16:00 | [16 empty] | 0 | 0
1.4 | 2 | Output detection to TV Remote Program | KP | 5 | 75 | 2020-02-14 |  | 2020-02-18 16:00 | [16 empty] | 0 | 0
1.4.1 | 2 | Send 1 if commercial break, 0 if return to program | ZT | 20 | 300 | 2020-02-14 |  | 2020-02-23 16:00 | [16 empty] | 0 | 0
1.4.2 | 2 | Pass through Mode value from System Remote to either mute (0) or vol. up/down (1) | ZT | 2 | 30 | 2020-02-14 |  | 2020-02-17 16:00 | [16 empty] | 0 | 0
2 |  | TV Remote Program | TM | 30 | 450 | 2020-01-30 | 2020-01-30 | 2020-02-15 | [16 empty] | 32 | 480
2.1 | 2, 3, 4 | Program receives input from Commercial Detection to trigger mute or vol up/down signal to TV | TM | 5 | 75 | 2020-02-06 | 2020-02-12 | 2020-02-10 16:00 | [16 empty] | 14 | 210
2.2 | 4 | Program will mimic the original Westinghouse TV remote provided | SF | 10 | 150 | 2020-01-30 | 2020-01-30 | 2020-02-05 08:00 | 2020-02-05 | [15 empty] | 6 | 90
X
2.2.1 | 4 | Program transmits Mute/Unmute to TV and TV mutes/unmutes | SF | 5 | 75 | 2020-02-04 | 2020-01-30 | 2020-02-08 16:00 | 2020-02-05 | [15 empty] | 6 | 90
X
2.2.2 | 4 | Program transmits vol. up/down to TV and TV increases/decreases in volume | TM | 10 | 150 | 2020-02-08 | 2020-01-31 | 2020-02-14 08:00 | 2020-02-05 | [15 empty] | 6 | 90
X
3 |  | System Remote | SF | 8 | 120 | 2020-02-18 | 2020-02-13 | 2020-02-27 | 2020-02-14 | [15 empty] | 4 | 60
X
3.1 | 5 | Start/Stop button on remote transmits signal to start and stop commercial detection program | SF | 3 | 45 | 2020-02-18 | 2020-02-13 | 2020-02-22 | 2020-02-14 | [15 empty] | 2 | 30
X
3.2 | 5 | Mode button transmit signal that toggles value in Commercial Detection to either mute TV or reduce volume by 50% | TM | 5 | 75 | 2020-02-22 | 2020-02-14 | 2020-02-26 16:00 | 2020-02-14 | [15 empty] | 2 | 30
X
4 |  | System Enclosure | SF | 7 | 105 | 2020-03-12 |  | 2020-04-01 | [16 empty] | 5 | 75
4.1 | 1, 5, 6, 7, 8 | Create Solidworks schematic | SF | 2 | 30 | 2020-03-23 |  | 2020-03-26 16:00 | [16 empty] | 5 | 75
4.1.1 | 1, 5, 6, 7, 8 | Record final dimensions of prototype | ZT | 2 | 30 | 2020-03-23 |  | 2020-03-26 16:00 | [16 empty] | 0 | 0
4.2 | 1, 5, 6, 7, 8 | Print & assemble the casing | ZT | 3 | 45 | 2020-03-27 |  | 2020-03-31 | [16 empty] | 0 | 0
5 |  | Integration & Testing | KP | 100 | 1500 | 2020-03-03 |  | 2020-04-10 | [16 empty] | 0 | 0
5.1 | 3, 5 | Commercial Detection Program successfully reads input from System Remote | ZT | 10 | 150 | 2020-03-03 |  | 2020-03-09 08:00 | [16 empty] | 0 | 0
5.2 | 2, 4 | Commercial Detection Program detects breaks and returns to programming | KP | 30 | 450 | 2020-03-09 |  | 2020-03-22 | [16 empty] | 0 | 0
5.3 | 2, 4 | Commercial Detection Program outputs detections successfully to TV Remote program | TM | 20 | 300 | 2020-03-09 |  | 2020-03-18 16:00 | [16 empty] | 0 | 0
5.4 | 4 | TV Remote Program successfully mimics Westinghouse TV Remote mute & vol. up/down functions | TM | 10 | 150 | 2020-03-18 |  | 2020-03-24 08:00 | [16 empty] | 0 | 0
5.5 | 1, 7, 8 | System fits into enclosure and does not impeed IR transmission & reception. | SF | 20 | 300 | 2020-04-01 |  | 2020-04-10 16:00 | [16 empty] | 0 | 0
5.6 | 6 | System Remote successfully starts & stops commercial detection program | ZT | 10 | 150 | 2020-03-03 |  | 2020-03-09 08:00 | [16 empty] | 0 | 0
6 |  | Commercial Detection Alternative | KP | 58 | 870 | 2020-04-03 | 2020-04-03 | 2020-04-24 | 2020-04-28 | [15 empty] | 238 | 3570
X
6.1 | P.1 | Program successfully imports .mp4 and detects black frames preemptively | KP | 20 | 300 | 2020-04-03 | 2020-04-03 | 2020-04-12 16:00 | 2020-04-19 | [15 empty] | 29 | 435
X
6.2 | P.2 | Program is able to split .mp4 file into multiple files based upon detections | ZT | 15 | 225 | 2020-04-12 | 2020-04-19 | 2020-04-20 | 2020-04-22 | [15 empty] | 22 | 330
X
6.3 | P.2 , P.3 | Program deletes commercial segments from directory | KP | 5 | 75 | 2020-04-12 | 2020-04-24 | 2020-04-16 16:00 | 2020-04-26 | [15 empty] | 5 | 75
X
6.4 | P.4 | Program merges show segments into a singular .mp4 file | ZT | 8 | 120 | 2020-04-12 | 2020-04-22 | 2020-04-17 16:00 | 2020-04-25 | [15 empty] | 7 | 105
X
6.5 | P.5 | Program only accepts .mp4 files, provides error message when given other file types | KP | 10 | 150 | 2020-04-03 | 2020-04-03 | 2020-04-09 08:00 | 2020-04-05 | [15 empty] | 8 | 120
X
TOTALS: |  |  |  | 383 | 5745 | [19 empty] | 167 | 2505